{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Plan1","Plan2","Plan3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Plan1","index":0,"n_rows":54,"n_cols":15,"rows_kept":54,"cut":false,"hidden":false,"merged":[[22,11,22,14],[0,0,0,14],[39,12,39,14],[37,11,37,13],[50,11,50,14],[23,11,23,14],[2,2,2,7],[1,0,1,14],[33,2,33,7],[12,11,12,14],[27,11,27,14],[29,11,29,14],[31,11,31,14],[28,11,28,14],[30,11,30,14],[32,11,32,14],[33,11,36,14],[53,11,53,12],[53,3,53,7],[53,0,53,2],[24,11,24,14],[25,11,25,14],[26,11,26,14],[38,11,38,14],[49,11,49,14],[51,11,51,14],[52,0,52,14]],"flags":["formulas_cached_only"]}
["Controle de conclusão recenso Parcelas Permanentes - Mês de Junho"]
[]
["Parc","Dia","Equipe executora",{"$nulls":5},"Outros","Integ","$ por int","Outra Atividade","Data","Equipe"]
["F13",1,null,null,"Eduardo","Noeli",null,null,null,2,37.5,"Chuva de sementes Dani","2009-06-04","Edison"]
["F14",2,null,null,"Eduardo","Noeli",null,null,null,2,37.5,"Chuva de sementes Dani","2009-06-04","Juninho"]
["F15",3,null,null,"Eduardo","Noeli",null,null,null,2,37.5,"Chuva de sementes Dani","2009-06-04","Ivaldo"]
["G13",1,"Juninho","Edison",null,null,null,"Ivaldo",null,3,25,"Viveiro Diana","2009-06-07","Ivaldo"]
["G14",2,"Juninho","Edison",null,null,null,"Ivaldo",null,3,25,"Coleta sementes Diana","2009-06-14","Sergio"]
["G15",3,null,"Edison",null,null,null,"Ivaldo",null,2,37.5,"Viveiro Diana","2009-06-06","Juninho"]
["H00",5,null,null,"Eduardo","Noeli",null,null,null,2,37.5,"Viveiro Diana","2009-06-07","Juninho"]
["H01",8,null,null,"Eduardo","Noeli",null,null,null,2,37.5,"Coleta e viveiro Diana","2009-06-13","Juninho"]
["H02",9,null,null,"Eduardo","Noeli",null,null,null,2,37.5,"Viveiro Diana","2009-06-30","Juninho"]
["H03",15,null,null,"Eduardo","Noeli",null,null,null,2,37.5]
["H04",17,null,null,"Eduardo","Noeli",null,null,null,2,37.5,"Integrante","Dias","$ por integ"]
["H05",18,null,null,"Eduardo","Noeli",null,null,null,2,37.5,"Edison",1,37.5]
["H06",19,null,null,"Eduardo","Noeli",null,null,null,2,37.5,"Eduardo",0,0]
["H07",22,null,null,"Eduardo","Noeli",null,null,null,2,37.5,"Ivaldo",2,75]
["H08",23,null,null,"Eduardo","Noeli",null,null,null,2,37.5,"Juninho",5,187.5]
["H09",27,null,null,"Eduardo","Noeli",null,null,null,2,37.5,"Noeli",0,0]
["H10",27,null,null,"Eduardo","Noeli",null,null,null,2,37.5,"Sergio",1,37.5]
["H11",28,null,null,"Eduardo","Noeli",null,null,null,2,37.5,null,"Total",337.5]
["H12",28,null,null,"Eduardo","Noeli",null,null,null,2,37.5]
["H13",29,null,null,"Eduardo","Noeli",null,null,null,2,37.5]
["I00",5,"Juninho","Edison",null,null,null,"Ivaldo",null,3,25,"Observações"]
["I01",5,"Juninho","Edison",null,null,null,"Ivaldo",null,3,25]
["I02",8,"Juninho",{"$nulls":4},"Ivaldo",null,2,37.5,"(1) A equipe manteve o ritmo de trabalho, mas"]
["I03",9,"Juninho",{"$nulls":4},"Ivaldo",null,2,37.5,"nesse mês tiveram muitos dias de chuva"]
["I04",15,"Juninho","Edison",{"$nulls":5},2,37.5]
["I05",17,"Juninho","Edison",{"$nulls":5},2,37.5,"(2) Edison faltou uma semana para completar estágio"]
["I06",27,"Juninho",{"$nulls":5},"Diana",2,37.5,"para formatura e mais uma semana por estar doente"]
["I07",27,"Juninho",{"$nulls":5},"Diana",2,37.5]
["I08",28,"Juninho",{"$nulls":5},"Diana",2,37.5,"(3) Eduardo e Noeli querem iniciar digitalização dados"]
["I09",29,"Juninho","Edison",{"$nulls":5},2,37.5]
["Parc","Dia","Equipe executora",{"$nulls":5},"Outros","Integ","$ por int"]
["I10",29,"Juninho","Edison",{"$nulls":5},2,37.5]
["J00",11,{"$nulls":4},"Sergio","Ivaldo",null,2,37.5]
["J01",13,{"$nulls":4},"Sergio","Ivaldo",null,2,37.5]
["J02",15,{"$nulls":4},"Sergio","Ivaldo",null,2,37.5,"Total parcelas cumpridas em Maio",null,null,48]
["J03",22,{"$nulls":4},"Sergio","Ivaldo",null,2,37.5]
["J04",16,null,"Edison",null,null,"Sergio","Ivaldo",null,3,25,null,"Total de parcelas"]
["J05",16,null,"Edison",null,null,"Sergio","Ivaldo",null,3,25,"Integrante","Em 2","Em 3","$ Total"]
["J06",24,{"$nulls":4},"Sergio","Ivaldo",null,2,37.5,"Diana",3,0,112.5]
["J07",24,{"$nulls":4},"Sergio","Ivaldo",null,2,37.5,"Edison",5,6,375]
["J08",25,"Juninho",null,null,null,"Sergio","Ivaldo",null,3,25,"Eduardo",17,0,637.5]
["J09",25,"Juninho",null,null,null,"Sergio","Ivaldo",null,3,25,"Ivaldo",15,8,837.5]
["J10",27,{"$nulls":4},"Sergio","Ivaldo",null,2,37.5,"Juninho",9,6,675]
["J11",27,{"$nulls":4},"Sergio","Ivaldo",null,2,37.5,"Noeli",17,0,637.5]
["J12",28,{"$nulls":4},"Sergio","Ivaldo",null,2,37.5,"Sergio",12,4,587.5]
["J13",28,{"$nulls":4},"Sergio","Ivaldo",null,2,37.5,null,null,"TOTAL",3862.5]
["J14",29,{"$nulls":4},"Sergio","Ivaldo",null,2,37.5]
["J15",29,{"$nulls":4},"Sergio","Ivaldo",null,2,37.5]
[]
[]
["Saldo final",null,null,"Total parcelas cumpridas em Junho",{"$nulls":4},47,null,3487.5,"Custo médio por parcela",null,75]

{"sheet":"Plan2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Plan3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}